## Slide 1: Group Project Final Presentation
Group 19
Dongge, Xi, Luan, Tenzin

## Slide 2: Outline
Project Demonstration
Initial Scope Vs. Final Product
What went well
What did not go well
Lessons Learnt

## Slide 3: Project Demonstration
A website on tourist attraction sites in Canberra
Technical Details:
  Built using ASP.NET framework
  Google Maps
  Picture Gallery
  Hosted on AWS EC2 instance running Debian
Website deployed at: http://54.70.241.11/
Deployment Manual: http://54.70.241.11/deployment_documentation.pdf

## Slide 4: Initial Scope Vs. Final Product
Sl. No. | Scope | Final Product
1 | Brief Description of place | ✔
2 | Location using Google Maps | ✔
3 | Picture Gallery | ✔
4 | Ability to post and view comments | ✖
5 | Deployment on server | ✔
6 | Deployment Manual | ✔

## Slide 5: Retrospective – What went well
What went well | Why | Impact
Communication | Using communication channel that all group members are familiar with Group became more cohesive | Able to keep track of everyone’s issues Faster resolution of issues
Project building and deployment | Use of automated build tools (visual studio) Experience in system administration from other units in UC | Able to deploy group project as per scope
Documentation | Previous experience in creating user document | Able to create deployment manual as per scope
Testing | Scope of testing was less due to the nature of project | 

## Slide 6: Retrospective – What did not go well
What did not go well | Why & what is the impact | What to do differently next time
Initial Plan | Did not undertake through planning process Schedule timeline, risk assessment etc. were estimates from verbal consensus amongst group members No clear requirement | Spend more time and effort in planning phase Learn and use schedule estimation methods
Initial skill assessment | Did not have a clear skill assessment Nobody knew how to implement some of agreed scope items | Discuss and document team members’ skill set before deciding on a project
Version control | Decided not to use VC due to lack of experience Problems integration individual works | Factor in time required to learn VC in project schedule
Could not implement all scope items | Lack of required skill Project not complete as per initial scope | Do proper planning and skill assessment Factor in time required to learn necessary skill in project schedule

## Slide 7: Lessons Learnt
Importance of planning phase
Clear idea of group’s skill set
Use version control in group projects
Learn required skill if it is not in the group’s skill set and include that time in project schedule
Team cohesiveness

## Slide 8: References
Wikipedia (http://en.wikipedia.org) - for use of materials under public domain or creative commons license

## Slide 9: Thank You